## Slide 1: IST687 Project Update #3
Agile Kanban Methodology
ADS Group 4
Jacob Dineen
Mason David
Mohamed Khalifa
Zhaowei Jiang
Kellie Mosely

## Slide 2: Kanban Board
BACKLOG | IN-PROGRESS | ANALYSIS | DEPLOYED
None | Final Presentation Final Analysis Final Interpretation Final Visualizations | SVM KSVM Naïve Bayes Association Rules NPS Linear Modeling Summary Statistics Findings | Data Cleansing Data Transformation Data Architecture Preliminary Data Analysis

## Slide 3: Team Page
Trello Link
Main Board:
https://trello.com/b/lXdbFrjQ/
Update 2 Board:
https://trello.com/b/zeJP8P5Q/update-3

## Slide 4: What’s the scope
file-> out-201501rv
Area of focus
  Demographic/ Behavior
  Amenities
  Hotel/Brand Classification
Geographical Scope = California, Arizona, Nevada, Utah, Colorado, New Mexico

## Slide 5: Business Question
What’s our target region?
Is there a relationship between audience demographics/behavior and NPS?
What specific criteria “amenities” contribute to higher NPS?
What recommendations can we provide to our clients to maximize the overall NPS?

## Slide 6: Overall Summary
Data Understanding | Preprocessing | Analysis | Testing | Communicating Results
 |  | 40% of time / 5 people | 40% of time / 5 people | 20% of time / 5 people
What is working well
Active Participation
Communication
Team Bonding
Brainstorming
Organization
Accomplishments this past period
Summary Statistics on Dataset
Expanded scope of project
Answered Business Questions
Calculated NPS Score
Built Models – Linear, SVM, KSVM, Naïve Bayes, Association Rules
Plans for next update
Create PowerPoint Presentation with findings presented in a way that is understandable to someone who isn’t data savvy.
Prepare Final Word Document with findings/analysis inclusive of R code to be sent to data science team leader.
Recommendation for client.
Issues / What is not working well
Fine tuning models.

## Slide 7: NPS Score

## Slide 8: Linear Modeling

## Slide 9: Descriptive Statistics

## Slide 10: Association Rule Mining

## Slide 11: SVMs

## Slide 12: SVMs Continued

## Slide 13: SVMs Continued